## 0
1 Product Management | 1 | TM0.011 | 11 |  | Market expectations
|  | TM0.011.01 | 11 | 1 | Market expectations defined? | * Describe the unmet or latent need of the market to our product which shall be addressed by the new Technology * Describe the value proposition that should be reached * When is expected to have the new technology available for the market? | MKT | PRG
| 2 | TM0.012 | 12 |  | Preliminariy Timeline & Project Set up
|  | TM0.012.01 | 12 | 1 | Preliminary timeline until TM1 (MRS release) and PM defined? | *Plan Resources from technology for the MRS Phase … to start with a Draft of the PRS * name Project Manager and key experts * define Timeline, when MRS is ready * dedicated Budget only if >100'000 EUR are required | MKT | PRG
2 Program Management | 1 | TM0.021 | 21 |  | Project Motivation Presentation
|  | TM0.021.01 | 21 | 1 | Technology idea, Project objectives and scope and value proposition defined? | * Define highlevel the scope of the technology development - What is the idea for the technology? - What is the goal of the Project and what is in and out of scope? - Which learnings we would like to have achieved? * Formulate your hypothesis why it is a real demand, Why AIXTRON can win and why it should be worth doing it | PRG | MKT
|  | TM0.021.02 | 21 | 2 | Program expectations defined ? | * Which product shall use the new technology? * Shall the new technology be handed over to and productized in a PEP or PCM Change (PDP-S)? * What is the expected TRL at handover? * What is the expected timeline until handover to the product? | PRG | MKT
|  | TM0.021.03 | 21 | 3 | Project Motivation Presentation /MO released | *All above mentioned items to be presented in ONE ppt to Project Steering Committee (PSC) -> MO template * PSC releases all above mentioned items w/ M0, no extra signatures needed
10 Controlling | 1 | TM0.101 |  |  | Project number
|  | TM0.101.01 | 101 | 1 | Project number assigned? | With M0 release the PSP number can be assigned | CTRL | PM

## 1
1 Product Management | 1 | TM1.011 | 11 |  | MRS (80%)
|  | TM1.011.01 | 11 | 1 | Which MRS items are not clear to the project team? | * Describe the gap in the market, i.e. the missing functions, not the solution concept. * Review MRS in Jira with the technology team for a common understanding, i.e., clarification of the degrees of freedom of technologies to define the solution * The content is sufficient for the project to start w/ first ideas and planning | MRS in JIRA | Product Marketing | Project Management
|  | TM1.011.01 | 11 | 1 | Are joint development partners foreseen? | * Do we need development partners? If so who? and when to involve (right from the beginning or only for qualification?) | MRS in JIRA | Product Marketing | Project Management
|  | TM1.011.02 | 11 | 2 | MRS-Baseline (80% maturity - 100% Scope) released? | * All MRS items are listed and "accepted" in Jira * 80% maturity accepted (at 100% Scope) * Release by sign-off of Jira-exported document by CEO, VP Marketing, VP Technology, VP Engineering, Program Manager, Produkt Manager | MRS document (pdf) extracted from Jira | Product Marketing | Project Management
3 Project Management | 1 | TM1.031 | 31 |  | Project planning M2
|  | TM1.031.01 | 31 | 1 | Project plan until TM2 created? | *Define the needed workpackages to TM2 (according checklist) and estimate the efforts * resources and staffing * timeline * estimation if budget of 100k€ is sufficent until TM2 -> if not PA is required. | Project plan | Project Management | Product Marketing
| 2 | TM1.032 | 32 |  | PA (Project Application)
|  | TM1.032.01 | 32 | 1 | Does the Phase from TM0 to TM2 require a budget >100k€? If so, has a PA until TM2 been signed yet? | *If initiatives directly related to the initialized project, such as LLI orders or early tests investigating general feasibility exceed the budget of 100k€ from TM0 to TM2 a preliminary project application is required. | PA template | Project Management | Controlling

## 2
1 Product Management | 1 | TM2.011 | 11 |  | MRS (100%)
|  | TM2.011.04 | 11 | 1 | MRS-Baseline (100% Maturity) released? | * MRS finalized by Marketing - All MRS items are listed and "accepted" in Jira - 100% maturity accepted (at 100% Scope) | JIRA | Product Management | Project Management
2 Program Management | 2 | TM2.021 | 21 |  | Technology Sponsorship
|  | TM2.021.01 | 21 | 1 | Did Project team agree on objectives and scope (incl. Definition of target TRL)? | Agreement between Program Manager & Project Manager (as representive of team) on objectives and scope. Program Mgr needs to make sure that TDP fits under program umbrella. | JIRA | Program Mgr | Product Mkt
|  | TM2.021.02 | 21 | 2 | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) | Program Management is accountable for regular update of project justification by answering the RWW questions: * REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution? *WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? | RWW Slide in TM2 presentation | Project Mgmt | Program Mgr | [18 empty] | *Product Management must test as good as possible if there is a real need at the market, i.e. is the problem we try to solve or the envisioend benefit real? AND if the target customers are willing to pay for our solution? *Program Management must assess as good as possible, if the added value we are aiming for,can be delivered with the new Technology.-> CAN WE WIN? , *Program Management must assess as good as possible, if is really worth it (spending reosurces and money) on this? * Note: and in case of internal value added, the project management also supports the is it real and can we win question *Is the technology development still on track to reach the goals set, i.e. review / assessment of the whole RWW
3 Project Management | 3 | TM2.031 | 31 |  | Project planning
|  | TM2.031.01 | 31 | 1 | Project plan for complete project defined? (incl. starting & end point, project strategy (e.g. # iterations) | * Project strategy defined - assumption of needed iterations of development cycles - internal development and/ or collaboration w/ externals - handover to productization - starting point and end point - TRL at project end (TRL5-> PEP & TRL>=6 -> PCM) * Project plan set up based on - work packages and efforts aligned w/ line managers - resources and staffing - summarized in a Work Breakdown Structure (WBS) * Budget for resources, external services, material and other costs * scheduling of Milestone Reviews incl. Previews 4 weeks ahead | *WBS templates for calculated hours per department (part of the PEP Dashboard) *Project plan (mpp) template (for the timeline of the work-packages), template from PMO *PA (xls), for budget Template from Controlling * Meisterplan (software) for resource allocation | Project Mgmt | Program Management (Technology Sponsor)
|  | TM2.031.02 | 31 | 2 | Which risks have not been listed and assessed yet? (project risks and PRS risk assessment) | * Conduct risk assessment and mitigation based on Jira items * conduct risk assessment and mitigation of remaining topics based on the dashboard | *JIRA (Software) (each Item has a risk analysis inlcluded) -> CRI rating *Project Risk rating in TEP Dashboard | Project Mgmt | Program Mgmt
| 3 | TM2.032 | 32 |  | PA (Project Application)
|  | TM2.032.01 | 32 | 1 | Project Application released? | Fill in the PA Template completely as per PA-instructions | *PA (xls), Template from Controlling | Project Mgmt | Controlling
| 3 | TM2.033 | 33 |  | PRS
|  | TM2.033.01 | 33 | 1 | Which parts of the MRS are not covered by the PRS? | *Translate all Marketing Requirements into Product Requirements *Using coverage level in JIRA *List requirments not covered in PRS *non-covered requirements to be presented in MRM (Milestone Release Meeting) | JIRA | Project Mgmt | Product Mkt
|  | TM2.033.02 | 33 | 2 | Which stakeholders have not yet defined their requirements? | * Identify and define stakeholders (= not part of the project team) -> Marketing, Quality, Service, Purchasing * Request stakeholders to provide their relevant requirements and their experience/lessons learned * Project Team to provide leassons learned * Workshop with the aim to jointly prioritize provided lessons learned and requirements from the different stakeholders ## if no Systems Engineer or Technologists from TechInnovation | Workshop w/ stakeholders, JIRA | Project Mgmt | Systems Engineering
|  | TM2.033.03 | 33 | 3 | PRS Baseline Released? | * All PRS requirements are entered in Jira * Review by Project team; if ok, Project manager or Systems engineer set requirement to "accepted" * All requirements must have status accepted (= requirement description done - not more) in Jira from all Stakeholders (TBD) -> defines baseline * Required signatures: TDP project team, Project Manager, Program Manager, Product Mgr, Mgr Technology Innovation *Signature to be performed directly in Jira using baselines | JIRA | Project Mgmt | Program Mgr
| 4 | TM2.041 | 41 |  | Proof of Concept Testing |  |  |  |  | 41 |  | Fast Learning Loops |  |  | TM3.041 |  |  | Fast Learning Loops |  |  | TM4.041 |  |  | Technology Qualification |  |  | 2
|  | TM2.041.01 | 41 | 1 | Which key questions (e.g. on feasibility/cost/strategic) are crucial for the project (so called red flags) and have not yet been answered? | * Indentify the real important questions on technical and economical feasibility which are a thread to the whole project needs to be answered as soon as possible * Proof-of-Concept testing - if beneficial, fast PoC tests can be initiated already in TM2 phase. - These tests can provide crucial input for project planning |  | Technology | Project Mgmt | 41 | 1 | Which key questions (e.g. on feasibility/cost/strategic) are crucial for the project and have not yet been answered? | Technology | Project Mgmt | TM3.041.01 | 41 | 1 | Which (key) functions / hypotheses are not proven yet by the learning loops? | Technology | Project Mgmt | TM4.041.01 | 41 | 1 | Final Technology Qualification review performed and TRL target achieved? | Technology | Project Mgmt | 3
|  | TM2.041.02 | 41 | 2 | For which key questions are no preliminary red flag test defined? | * Plan simple but convincing feasibility tests to mitigate the red flags * Start testing immediately |  | Technology | Project Mgmt | 41 | 2 | For which key questions are no preliminary red flag test defined? | Technology | Project Mgmt | TM3.041.02 | 41 | 2 | Which red flag test are not passed? | Technology | Project Mgmt | [6 empty] | 4
| 4 | TM2.042 | 42 |  | Technology Development (Problem-Analysis, first ideas and solution space)
|  | TM2.042.01 | 42 | 1 | Which parts of the problem has not been analyzed and formulated in a problem statement yet? | * systematic analysis of the problem/ of the technical system - what is the real problem? - What is the root cause? - Which parameters can be used to improve the technology? - what are the boundary conditions? * clear problem statement | to be selected according the problem: * Root cause analysis / 5WHY, Ishikawa, Function analysis, function model etc. * problem statement as ppt slide | Technology | Project Mgmt
|  | TM2.042.02 | 42 | 2 | Has first ideas been gathered? | * State of the art analysis ->Before developing something new the state of the art has to be understood * Brainstorming of first ideas / collecting ideas from former projects -> Be careful: This does not replace a systematic concept development | Idea Portfolio | Technology | Project Mgmt
|  | TM2.042.03 | 42 | 3 | For which technologies could a solution path not yet be defined? | * TRL and feasibility assessment of first ideas * Pre-selection of most promising ideas * sketch technical solution path for Technology development -> serves as basis for planning | Idea Portfolio + ppt | Technology | Project Mgmt
|  | TM2.044 | 44 |  | Effects on Software
|  | TM2.044.01 | 44 | 1 | For which key functions and key components has the influence on software not been checked? | * Check if the drafted solution path requires software development or adaptions * incorporate into planning accordingly | Project plan | Software Development | Project Mgmt
4. Technology & Engineering | 6 | TM2.051 | 51 |  | IP Overview
|  | TM2.051.01 | 51 | 1 | IP Overview created (State of the Art)? | * IP landscape research based on idea portfolio * overview created about relevant IP in this field | Infopatent | Intellectual Property | Technology
|  | TM2.051.02 | 51 | 2 | FTO for initial ideas / solution space? | * IP reviewed by Project team - which ideas can be used? - which patents are blocking? * FTO for solution space. If not new ideas has to be developed. | template from IP | Intellectual Property | Project Mgmt
| 7 | TM2.061 | 61 |  | FMEA & Quality plan
|  | TM2.061.01 | 61 | 1 | if target TRL >=5 LLI Supplier qualification: potential analysis completed and (if required) measures defined? | If the targeted TRL of the new Technology is >=5 (at the next iteration loop) it is necessary to do verify, if the selected supplier can deliver the expected quality. This is covered by the potential analysis | template from part quality | Quality | Project Mgmt
| 6 | TM2.071 | 71 |  | Supply Chain & Procurement for Development
|  | TM2.071.01 | 71 | 1 | Which components or materials with long lead times need an early order? | Long Lead Item (LLI) list w/ suppliers created |  | Purchasing | Project Mgmt
5 IP
6 Quallity
7 Purchasing
8 Operations
9 Service

## 3
2 Program Management | 2 | TM3.021 | 21 |  | Technology Sponsership
|  | TM3.021.01 | 21 | 1 | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) | Program Management is accountable for regular update of project justification by answering the RWW questions: * REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution? *WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? |  | Project Mgmt | Program Mgr
3 Project Management | 3 | TM3.031 | 31 |  | Technical & economic viability assessment & Project & Risk Mamagement
|  | TM3.031.01 | 31 | 1 | Project plan (timeline and budget) updated until TM4? | * Monthly update of project plan expected - scope & early testing - number of development loops - timeline - resources - budget - test cases and need test rigs - required lab time & resources * Project manager updates the timeline based on updated the timelines of work packages (should be done within the team) * Including Software Release plan due to project timeline * Communicate the effects of changes in the project plan from the current phase to everyone affected by the impact * Milestone Preview (4-6 Weeks prior to Review) | Project plan | Project Mgmt | Program Mgr
|  | TM3.031.02 | 31 | 2 | Which risks are pending regarding assessment and mitigation? (Project and PRS risks) | *Alignment PRS with results of the current phase, e.g. test results, FMEA Measures, built issues, etc. * Update risk assessment and mitigation based on Jira items * Update risk assessment and mitigation of remaining topics based on the dashboard | *Jira (Software) | Project Mgmt | Program Mgr
|  | TM3.031.03 | 31 | 3 | Which information are missing to give a commitment to deliver the new technology with TRL5 on time? | Assess how much confidence we gained to achieve TRL5 on time. Which investigatios or test results are missing to give a commitment? Which uncertainties remain? Clearly show, which results gives conficence to deliver on time. |  | Project Mgmt | Program Mgr
|  | TM3.031.04 | 31 | 4 | Which items of the handshake to PEP / PCM are not yet defined in the handover list? | The technology needs to be handed over properly to a either a PCM or PEP for productization. All items needs to be defined in the TDP Handover List, as - links to a technical file describing the developement of the technology and related learnings, - all design documents (BOM, drawings) - Supporting documents or TAs for assembly and integration - Shop floor test instructions - Part quality and supplier information - SW documentation ... | TDP Handover List Template (tbd) | Project Mgmt | Program Mgr
|  | TM3.033 | 33 |  | PRS |  | Template from Quality
|  | TM3.033.01 | 33 | 1 | Which PRS items are not yet updated? | * It is likely that learnings during technology development lead to changes or refinement of requirements in PRS. Hence, with each development loop the requirements should be reviewed and updated if required | JIRA /PRS | Technology | Project Mgmt
|  | TM3.033.02 | 33 | 2 | Which PRS items are not yet linked to a test case? | * Define a relevant test case for technical PRS items in Jira * Ensure the required test environment in coordination with the parties concerned, such as the laboratory * Ensure an all encompassing test concept for qualification phase to ensure fullfillement of each requirement of the PRS | JIRA and test plan (format depends on purpose) | Technology | Project Mgmt
|  | TM3.033.03 | 33 | 3 | Which test cases have not been passed yet? | Evaluation of test results and comparison with MRS and PRS *root cause analysis for unsuccessfull test results *create back log list for further improvement *open issues from the back log list must be assigned and solutions developed | JIRA | Technology | Project Mgmt
|  | TM3.041 | 41 |  | Fast learning loops
|  | TM3.041.01 |  |  | Which (key) functions / hypotheses are not proven yet by the learning loops? | * Make sure that the tests / investigations answering the key questions are handled with priority * each key question shall be answered and well documented in a Technical Investigation Report | Technical Investigation Report (template in ppt) | Technology | Project Mgmt
|  | TM3.041.02 |  |  | Which red flag test are not passed? | * Analyse why tests have not been passed * Derive learning * Review and update risk analysis accordingly |  | Technology | Project Mgmt
| 4 | TM3.042 | 42 |  | Technology Development
|  | TM3.042.01 | 42 | 1 | Which individual concepts for the required functions are not yet finalized and aligned with each other and the overall concept? | * Create a Functional model for the new Technology or provide Functional Analysis for the given problem * Develop various solution alternatives for the individual functions -> Morphological Box * Combine individual solutions into a few meaningful overall concepts * Assessment of concepts based on defined criteria and selection of most promising * Work out the concept as far as needed to answer PRS coverage, considering - key requirements and solved key questions - expected process performance, - integration into target system and interfaces, - Manufacturability, - assembly and test - software - Serviceability | Recommended but not mandatory: Functional mode/structure Morphological Box NWA (Utility Value analysis), pairwise comparison or similar concept presentation | Technology | Project Mgmt
4 Technology & Engineering |  | TM3.042.02 | 42 | 2 | Which PRS items are not fullfilled by the concept? | * Check if the Concept fulfills all PRS requirements * Document results and degree of fullfillment -> as input for Concept Review Meeting | Concept Review presentation | Technology | Project Mgmt
|  | TM3.042.03 | 42 | 3 | Which concept review actions are still open? | * Conduct Concept Review Workshop with experts and relevant stakeholders * Review the complete concept on component level - Concept alternatives checked - Feasibility of key functions checked - Preliminary Supplier shortlist developed - Make or buy decided * Concept Risk Review-Event conducted * Concept by Program& Product Marketing approved * Planning & Risk Mitigation Event conducted * Define open actions | Concept Review template | Technology | Project Mgmt
|  | TM3.042.04 | 42 | 4 | Which Technological Learnings are not documented in a technical investigation report? | Document the key learnings in a comprehensive Technical Investigation Report | Technical Investigation Report (template in ppt) | Technology | Project Mgmt
| 4 | TM3.043 | 43 |  | Design review & release (if target TRL >=5)
|  | TM3.043.01 | 43 | 1 | Which individual designs according to Engineering BoM are not yet finalized? (if TRL >= 5) | Design for the whole technology is done, including * all CAD models * calculations and simulation reports * interfaces defiend and checked * Changes in basic documents updated and released: Gas-mixing-circuit, cooling circuit, vacuum circuit, floor plan, E-Plan, Network System List (NSL) * Supplier feedback on parts design collected, assessed and implemented * BoM cost estimation for design |  | Technology | Project Mgmt
|  | TM3.043.02 | 43 | 2 | Which PRS items are not fullfilled by the designed Technology? | * Check if the design fulfills all PRS requirements * Document results and degree of fullfillment -> as input for Design Review Meeting |  | Technology | Project Mgmt
|  | TM3.043.03 | 43 | 3 | Which critical design review actions are still open? | * Conduct Design Review Workshop with experts and relevant stakeholders * Review the complete design on component level - Feasibility of key functions checked - Supplier shortlist developed * Design FMEA input considered * Define open actions | Design Review template | Technology | Project Mgmt
|  | TM3.043.04 | 43 | 4 | Which departments have not yet released the design? | *All critical actions form design review are done * Minor actions are planned in further developement * Design released by whole TDP team and Program Mgr, Sen Mgr TechDev |  | Project Mgmt | Program Mgmt
| 5 | TM3.044 | 44 |  | Software for development
|  | TM3.044.01 | 44 | 1 | Which software packages for development and testing are not available? | * Check software releases available for the project * Define SW features and release version (What&When?) * If new software is needed for the project, update aligned timeline with the SW Project Management including releases for backlog topics
|  | TM3.051 | 51 |  | IP Update
|  | TM3.051.01 | 51 | 1 | LoD (List of Differences?) completed? | All technical differences compared to the state fo the art (own technology as well as foreign technology) has been identified and listed | List with detailed description of differences (ppt) | Technology | Intellectual Property
|  | TM3.051.02 | 51 | 2 | FTO for all identified solutions ? | - LoD (List of Differences?) defined? - IP Targets defined? - Can we achieve IP protection? - Do all identified solutions have Freedom to operate? |  | Intellectual Property | Project Mgmt
| 6 | TM3.061 | 61 |  | FMEA & Qualityplan
|  | TM3.061.01 | 61 | 1 | Concept FMEA conducted and measures implemented? (TRL4: only high level) | * Conduct Concept FMEA for the Technology ( for TRL4 only high level is needed) * Define mitigation measures * implementation of critical measues * Create a timeline and mitigation plan for those that are not yet implemented | Plato requried w/ TRL5 | Quality | Project Mgmt
|  | TM3.061.02 | 61 | 2 | If TRL>=5: Which design elements are not considered in the D-FMEA and which D-FMEA measures are not implemented? | *Update Design FMEA *Implement Design FMEA *Check all Design-FMEA, i.e., on part level, measures for their status (Desing FMEA on part level) *Create a timeline and mitigation plan for those that are not yet implemented | Plato | Quality | Project Mgmt
|  | TM3.061.03 | 61 | 3 | Which crititical parts do not have a 100% verification of dimensions + functional test (pre-sample)? If Final design loop: FSR required. | * Define / update a list of critical components * 100% verification of dimensions for all critical components * funtional tests done for functional units * If Final design loop: FSR required | Overview list and templates from Quality | Quality | Project Mgmt
|  | TM3.061.04 | 61 | 4 | If TRL>=5: Which suppliers have not been qualified yet? Which of them do not have the potential to be qualified? | * potential analysis completed * measures defined, incl. status to ISO 9001 | Overview list and templates from Quality | Quality | Project Mgmt
| 7 | TM3.071 | 71 |  | Supply Chain & Procurement for Qualification
|  | TM3.071.01 | 71 | 1 | Supplier selection aligned with Purchasing? | * List of suppliers defined * Aligned w/ purchasing |  | Technology | Purchasing
|  | TM3.071.02 | 71 | 2 | Prototype procurement completed (per Loop)? | * all parts needed for testing of the current development loop are available |  | Purchasing | Project Mgmt
| NEW | TM3.071.03 | 71 | 3 | Which stakeholder requirements from Purchasing are not defined yet? (with TRL5) | * Review current concept w/ Purchasing * Purchasing to provide their relevant requirements |  | Purchasing | Project Mgmt
| 6 | TM3.081 | 81 |  | Operations
|  | TM3.081.01 | 81 | 1 | Which stakeholder requirements from Operations are not defined yet? (with TRL5) | * Review current concept w/ Operations * Operations to provide their relevant requirements |  | Operations | Project Mgmt
5 IP | 6 | TM3.091 | 91 |  | Service
|  | TM3.091.01 | 91 | 1 | Which stakeholder requirements from Service are not defined yet? (with TRL5) | * Review current concept w/ Service * Service to provide their relevant requirements |  | Service | Project Mgmt
6 Quallity
7 Purchasing
8 Operations
9 Service

## 4
2 Program Management | 21 | TM4.021 | 21 |  | Technology Sponsorship
|  | TM4.021.01 | 21 | 1 | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) | Program Management is accountable for regular update of project justification by answering the RWW questions: * REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution? *WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? |  | Project Mgmt | Program Mgr
3 Project Management | 3 | TM4.031 | 31 |  | Project planning
|  | TM4.031.01 | 31 | 1 | Which risks are pending regarding update of assessment and mitigation? (Project and PRS risks) | *Alignment PRS with results of the current phase, e.g. test results, FMEA Measures, built issues, etc. * Update risk assessment and mitigation based on Jira items * Update risk assessment and mitigation of remaining topics based on the dashboard |  | Project Mgmt | Program Mgr
|  | TM4.031.02 | 31 | 2 | Lessons learned done and communicated? | * lessons Learned session with project team and relevant stakeholders done * results documented and communicated |  | Project Mgmt | Program Mgr
|  | TM4.031.03 | 31 | 3 | Which stakeholders have not yet released the handover list? | *A Handover list completed * List of open issues assigend to responsible (supplier in the phase of productization) * all project closing relevant tasks fulfilled * sign-off by customer | TDP Handover List Template (tbd) according to TM3.031.04 | Project Mgmt | Program Mgr / PEP PM
| 4 | TM4.033 | 33 |  | PRS
|  | TM4.033.01 | 33 | 1 | Which PRS elements have not been qualified? | *check final qualification status on PRS Level |  | Technology | Project Mgmt
|  | TM4.033.02 | 33 | 2 | Which test cases have not been passed yet? | Evaluation of test results and comparison with MRS and PRS *root cause analysis for unsuccessfull test results *create back log list for further improvement *open issues from the back log list must be assigned and solutions developed |  | Technology | Project Mgmt
|  | TM4.041 | 41 |  | Technology Qualification
|  | TM4.041.01 |  | 1 | Final Technology Qualification review performed and TRL target achieved? | * conduct Review of all qualification results * identify gaps to targeted TRL * define measures * re-iterate development if needed |  | Technology | Project Mgmt
|  | TM4.041.02 |  | 2 | If target TRL7: customer feedback received | * tested at customer and feedback received e.g. wishes for product improvememt |  | Technology | Project Mgmt
|  | TM4.042 | 42 |  | Technology Development - achieving TRL5/6 and documentation
|  | TM4.042.01 |  | 1 | Final design report released? | * Final design reported created/updated (shows final design) * released | ppt | Technology | Project Mgmt
|  | TM4.042.02 |  | 2 | Which technological learnings are not documented in the Technology Development File? | * update of Technical Development File report by qualification results and latest learnings (shows design incl. all relevant learnings - to preserve the knowledge) | Technology Development File | Technology | Project Mgmt
|  | TM4.042.03 |  | 3 | Which parts of the documents according handover list are still missing? (e.g. BoM, models, drawings, Work instructions) | * review items of handover list individually with receiwing project/customer * list is complete | handover list | Technology | Project Mgmt
| 44 | TM4.044 | 44 |  | Software for qualification
|  | TM4.044.01 | 44 | 1 | Which software packages for qualification or productization are not available? | *Update check of software releases available for productization |  | Software Development | Project Mgmt
| 46 | M4.051 | 51 |  | IP Update
|  | TM4.051.01 | 51 | 1 | LoD reviewed and updated? | * Make sure that LoD is up to date |  | Technology | Intellectual Property
|  | TM4.051.02 | 51 | 2 | FTO reviewed and updated? | * Make sure that FTO for the whole technology exists |  | Intellectual Property | Project Mgmt
6 Quallity | 61 | TM4.061 | 61 |  | FMEA & Quality plan
|  | TM4.061.01 | 61 | 1 | D-FMEA finalized and actions executed? | *Update Design FMEA *Check all Design-FMEA, i.e., on part level, measures for their status (Desing FMEA on part level) *Create a mitigation pactions which needs to be considered in further developemnt /productization |  | Quality | Project Mgmt
|  | TM4.061.02 | 61 | 2 | Which First Sample Reports (FSR) are not released? | *verification of the FSR from technology and quality together *decision for release or release with condition or rejection |  | Quality | Project Mgmt
|  | TM4.061.03 | 61 | 3 | If TRL>=5: Which suppliers have not been qualified yet? | Updates of * potential analysis * measures defined, incl. status to ISO 9001 to be followed up in productization | Overview list and templates from Quality | Quality | Project Mgmt
7 Purchasing | 71 | TM4.071 | 71 |  | Supply Chain & Procurement for Productization prepared
|  | TM4.071.01 | 71 | 1 | Procurement prepared for Productization | * Long Lead items for Productization identified * All documents are prepared for order * or in follow up project |  | Purchasing | Project Mgmt
10 | 111 | TM4.101 | 101 |  | Project Controlling
|  | TM4.101.01 | 101 | 1 | Project Costs validation done? | * validation of spent project costs |  | Controlling | Project Mgmt
Note on F21: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: Technology Protection plan is missing?

## Overview Deliverables (hidden)
Deliverables and Suppliers
| “Voice of Customer” | Initialization | Specification | Concept | Design | Prototyping | Ramp up | Customer | Ramp up | Series
[7 empty] | Pre-Series | Qualification | Series prod. | Production
Product Management (*incl. Project Plan till M1) | Product Idea: Value Proposition | Marketing Requirements (MRS) | Variances & Options (082.01) (from Customers' Perspective) | Product Concept (M3.031.03) |  |  |  | Marketing Documents
| Market and tier 1 customers | Key Customers | Key Customers for qualification |  | Customer agreements - ideally prototype contracts (incl. Produkt-Brief)
Market entry target timeline
|  |  |  | Feedback from key customers and development partners | External Feedback on design
Design Review Meeting (DRM) - NPI Manager involved
Progamm Management |  |  | Design Strategy
Project Management | Timeline till M1 | Timeline till M2 | Timeline till M8 | Update Project Plan | Update Project Plan | Update Project Plan | Update Project Plan | Update Project Plan | Project review & closure
(*Responsibility for Project Plan (PP) until M1 by Product Management) | Budget till M1 | Budget till M2 | Budget till M8
| Project manager to be named | Ressources | Scope till M8
|  | Work packages | WBS |  |  |  |  | Qualified PRS elements (= Product Qualification?) | Product maturity
Project Application (PA)
Variants and Options (or by Proj. Mgt?)
[6 empty] | Risk assessment & mitigation plan - 3rd ATP - 4th ATP (JDP / JEA) spec |  |  | Standard requirement updates (Lessons Learnd)
|  |  | -> Handshake all Departments! | Prototype Change Management due to LLI |  | as: Prepare Series Change Management |  |  | Continuous Improvement Process (CIP) Topics definde and handed over
Relevant Departments: | assign to each department
- Product Management / Program Management
- Project Managmeent |  |  | Product requirements (PRS) |  |  | 4th ATP |  |  | - Standard Requirements update -> link with Lessons Learned? (Template?)
Technology Readiness Level (TRL) 5
- Technology (all teams) * System Engineering * Mechanic.- & Electronic. Engineering * SW-Engineering * Process Development * Intelectuall Property * Safety * Documentation |  |  | Product requirements (PRS) | Individual Concepts (or by CE?) (=Product Concept (M3.031.03) | Individual Designs |  |  | Qualified PRS elements
Variants and Options (or by Proj. Mgt or by Op. Engin.?)
|  |  |  | Learning Loops (or by CE?) | Learning Loops & feasibility verfication
Test of Design Phase Test Case
Prototype work instructions
Prototype references on design status
- Operatonal Engineering & Production |  |  | Lessons Learned from previous projects - Product - Technology - Purchase Op Eng Service IP Quality Documentation safety
|  |  | Protype requirements Internal and external prototype - for pre-series maturity (M6) - to qualify product (M7) | Feasibility Checks
Variants and Options (or by Proj. Mgt or by Technology?)
|  |  |  | Product Concept (M3.031.03) | Design Review Meetint (DRM) | 1st ATP
- Purchasing |  |  |  |  | Design Review Meetint (DRM)
- Manufacturing
- Quality |  |  |  | Product Concept (M3.031.03) | Design Review Meetint (DRM)
- Service |  |  |  | Product Concept (M3.031.03) | Design Review Meetint (DRM)
- Sales
- NPI
- Core Team / CE Team |  |  | Relevant Learning Loops (Template?) | Learning Loops (or by Technology?)
|  |  |  | Individual Concepts (Tech. Or CE?) | (Individual Designs)
|  |  | Testing Key Functions feasibility |  | Test cases for PRS-/TRS elements (incl. Instructions) |  | Test Test-Cases for M5 | Qualified PRS elements
[5 empty] | (Results of testing Design-Phase-Test-Cases) | Target reproducibility and robustness criterias (or by Proj. Mgt?) |  | Passed Test Cases completed | Target reproducibility & robustness
Technology | see section above
- System Engineering |  |  | Functional Model & Context Diagram |  | TRS |  |  | - Product Qualitfication
|  |  | Architecture | Architecture
TRS
Test Cases - Design Phase - after M4
Functional BoM structure
|  |  |  | Fullfillness check on PRS Item level | Fullfillness check on PRS Item level
- Mechanical Engineering
- Electronical Engineering
- Software Engineering |  |  |  | Software Requirements (from key functions & - components) | Software packages available | SW for external Prototype released |  | Released Software
- Process Development |  |  |  | epi-process impact |  | 3rd ATP
- Intellectual Property |  |  | - State of the art | IP Targets | IP Targets | Patent Office Application
|  |  |  | List of Differences (LoD)-Items | LoD Items
- Safety |  |  |  | Safety and risc analysis
- Documentation | [5 empty] | Documentation - Documents for Customer for NPI - Installation & Service Doc. Intern - Customer training - Product conformity certification | Documentation -OEM manuals, data sheets and certification -Assembly drawings -Basic documentation -BoM -Recommended spare parts -Operations and maintenance manual -Electrical documentation -Mechanical documentation -Software documentation - Installation & Service (intern) | Documentation updated Customer Training documents finalized | Finalized Documentation
Operational |  |  | Prototype requirements | Manufacturing concept | Manufacturability - Asssembly concept - Transport concept - Packaging concept - Dissasembly concept | Manufacturability - online testprototcol - tests and documents | Parts of te manufacturing concpept validated |  | Final manufacturing concept
|  |  |  | Variants & Options | Variants & Options |  | Variants & Options |  | Variants & Options
[6 empty] | 1st ATP for external Prototype |  |  | Series-reference-BoM incl. Variants and options
Trained production launch team
[7 empty] | Pre-series reference & work instruction |  | Series work instruction
[7 empty] | Online Testprotocoll updated | Online Testprotocoll updated
NPI | [5 empty] | Customer Training scheduled | NPI Management ready for start of pre-series production
Open isseus out of the SPM Kick off
Final ATP for key customers
Quality |  |  |  | Quality Concept | Quality Plan |  | Updated Quality Plan |  | Fulfilled Quality Plan
|  |  |  | Qualification of LLI Suppliers | Supplier Qualification | First Sample Report (FSR)
|  |  | Risk assessment and mitigation for PRS Items | saftey and risk analysis
|  |  |  | check PRS items for risks and mititgation | Update check of risk and mitigation on PRS | Update check of risk and mitigation on PRS | Update check of risk and mitigation on PRS
[5 empty] | First Sample Report (FSR) Including P-FMEA for critical parts | First Sample Report (FSR) | FSR Update
|  |  | Measurements for FMEA’s (incl.assessm. robustness design) | System FMEA - concept elements - measures | Design FMEA (incl. Measures implemented) | Executed Design FMEA | Design FMEA updated & executed
Process FMEA measures implemented
Purchasing |  |  | order parts for learning loops | Supply Chain Concept - make or buy - single /multiple source | Update "ordering" - parts for qualitfication |  |  |  | -Supply Chain Ramp up
|  |  |  | Long List Items (LLI) | Project safety stock defined | Stock and storage strategy | Production safety stock and storage |  | Ordered series parts
|  |  |  | List of critical components & suppliers | Reviewed critical parts for DfM
|  |  |  | Suppliers "qualificaton" (& selection) | Suppliers - selection - business agreements | Manufacturability agreement supplier | Updated supplier business agreements | Confirm that existing supplier business agreement are still valid for ramp-up (ramp-up according to business plan)? | Updated supplier business agreements
Service |  |  |  | Service Concept | Impact on customer facility | Customer Facility readiness |  |  | Customer
[5 empty] | Spare Parts List |  |  | Recommended spare parts and expert parts confirmed
[5 empty] | Service Test Protocol | Service test protocol (ticketing system) |  | updated service test protocol
[6 empty] | Readiness for external Prototype installation |  | Confirmed installation process
External Product qualification
[5 empty] | Training (Plan/System) | Service Training content |  | Regional Service team trained | Training-dedicated series system available & trained team
Sales | [6 empty] | Sales Documents | Finalzed Sales Documents *Feature and option list *appendix *cost per feature *prepare templates for quotation
Controlling |  | Business Case | Business Case | Update Business Case | Update Business Case | Update Business Case | Update Business Case | Update Business Case
|  | incl. target COGS | (target & estimated COGS) | COGS (cost estimates based on defined costs) | COGS based on suppliers offer |  |  |  | Updated COGS
M2
M3
M4
M7
M1
MRS
release .
PRS
release .
Concept
release .
Design
release .
Pre-series
release .
M6
Customer
Qualification .
achieved
M8
Series
Maturity . achieved
M5
External
Prototype . shipment .
M0
Project
initialization .
M9
End of production .
End of
service .
M10

## Dropdown (hidden)
Flag
n/a
Green
Yellow
Red