## Upload_Template
Project Key | Issue Type | Summary | Key | Description | Reporter | PIP - Customer | PIP - Supplier | Fix Version/s | Epic Link | Epic Name | Epic Name Reference for Epic Linking
| Epic | Technology Sponsorship - M4 | [5 empty] | PIP Milestone 4 |  | Technology Sponsorship - M4
| Deliverable | TM4.021.01 - TM4.021.01 |  | Program Management is accountable for regular update of project justification by answering the RWW questions: * REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution? *WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  |  | Technology Sponsorship - M4
| Epic | Project planning - M4 |  | * Do we need development partners? If so who? and when to involve (right from the beginning or only for qualification?) |  | Project Management | Product Marketing | PIP Milestone 4 |  | Project planning - M4 | MRS (80%) - M1
| Deliverable | TM4.031.01 - TM4.031.01 |  | *Alignment PRS with results of the current phase, e.g. test results, FMEA Measures, built issues, etc. * Update risk assessment and mitigation based on Jira items * Update risk assessment and mitigation of remaining topics based on the dashboard |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  |  | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) - M4
| Deliverable | TM4.031.02 - TM4.031.02 |  | * lessons Learned session with project team and relevant stakeholders done * results documented and communicated |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  | Project planning M2 - M1 | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) - M4
| Deliverable | TM4.031.03 - TM4.031.03 |  | *A Handover list completed * List of open issues assigend to responsible (supplier in the phase of productization) * all project closing relevant tasks fulfilled * sign-off by customer |  | Program Mgr / PEP PM | Project Mgmt | PIP Milestone 4 |  | Project planning - M2 | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) - M4
| Epic | PRS - M4 |  | The technology needs to be handed over properly to a either a PCM or PEP for productization. All items needs to be defined in the TDP Handover List, as - links to a technical file describing the developement of the technology and related learnings, - all design documents (BOM, drawings) - Supporting documents or TAs for assembly and integration - Shop floor test instructions - Part quality and supplier information - SW documentation ... |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  | PRS - M4 | Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) - M3
| Deliverable | TM4.033.01 - TM4.033.01 |  | *check final qualification status on PRS Level |  | Project Mgmt | Technology | PIP Milestone 4 |  | PRS - M3 | Project planning - M4
| Deliverable | TM4.033.02 - TM4.033.02 |  | Evaluation of test results and comparison with MRS and PRS *root cause analysis for unsuccessfull test results *create back log list for further improvement *open issues from the back log list must be assigned and solutions developed |  | Project Mgmt | Technology | PIP Milestone 4 |  | PA (Project Application) - M2 | Project planning - M4
| Epic | Technology Qualification - M4 |  | * Define a relevant test case for technical PRS items in Jira * Ensure the required test environment in coordination with the parties concerned, such as the laboratory * Ensure an all encompassing test concept for qualification phase to ensure fullfillement of each requirement of the PRS |  | Project Mgmt | Technology | PIP Milestone 4 |  | Technology Qualification - M4 | Technical & economic viability assessment & Project & Risk Mamagement - M3
| Deliverable | TM4.041.01 - TM4.041.01 |  | * conduct Review of all qualification results * identify gaps to targeted TRL * define measures * re-iterate development if needed |  | Project Mgmt | Technology | PIP Milestone 4 |  | PRS - M2 | Which risks are pending regarding update of assessment and mitigation? (Project and PRS risks) - M4
| Deliverable | TM4.041.02 - TM4.041.02 |  | * tested at customer and feedback received e.g. wishes for product improvememt |  | Project Mgmt | Technology | PIP Milestone 4 |  | Fast learning loops - M3 | Which risks are pending regarding update of assessment and mitigation? (Project and PRS risks) - M4
| Epic | Technology Development - achieving TRL5/6 and documentation - M4 |  | * Make sure that the tests / investigations answering the key questions are handled with priority * each key question shall be answered and well documented in a Technical Investigation Report |  | Project Mgmt | Technology | PIP Milestone 4 |  | Technology Development - achieving TRL5/6 and documentation - M4 | Project plan (timeline and budget) updated until TM4? - M3
| Deliverable | TM4.042.01 - TM4.042.01 |  | * Final design reported created/updated (shows final design) * released |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Lessons learned done and communicated? - M4
| Deliverable | TM4.042.02 - TM4.042.02 |  | * update of Technical Development File report by qualification results and latest learnings (shows design incl. all relevant learnings - to preserve the knowledge) |  | Project Mgmt | Technology | PIP Milestone 4 |  | Technology Development - M3 | Lessons learned done and communicated? - M4
| Deliverable | TM4.042.03 - TM4.042.03 |  | * review items of handover list individually with receiwing project/customer * list is complete |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Lessons learned done and communicated? - M4
| Epic | Software for qualification - M4 |  | * Check if the Concept fulfills all PRS requirements * Document results and degree of fullfillment -> as input for Concept Review Meeting |  | Project Mgmt | Technology | PIP Milestone 4 |  | Software for qualification - M4 | Which risks are pending regarding assessment and mitigation? (Project and PRS risks) - M3
| Deliverable | TM4.044.01 - TM4.044.01 |  | *Update check of software releases available for productization |  | Project Mgmt | Software Development | PIP Milestone 4 |  | Technology Development (Problem-Analysis, first ideas and solution space) - M2 | Which stakeholders have not yet released the handover list? - M4
| Epic | IP Update - M4 |  | Document the key learnings in a comprehensive Technical Investigation Report |  | Project Mgmt | Technology | PIP Milestone 4 |  | IP Update - M4 | Which risks are pending regarding assessment and mitigation? (Project and PRS risks) - M3
| Deliverable | TM4.051.01 - TM4.051.01 |  | * Make sure that LoD is up to date |  | Intellectual Property | Technology | PIP Milestone 4 |  | Design review & release (if target TRL >=5) - M3 | PRS - M4
| Deliverable | TM4.051.02 - TM4.051.02 |  | * Make sure that FTO for the whole technology exists |  | Project Mgmt | Intellectual Property | PIP Milestone 4 |  |  | PRS - M4
| Epic | FMEA & Quality plan - M4 |  | * Check if the design fulfills all PRS requirements * Document results and degree of fullfillment -> as input for Design Review Meeting |  | Project Mgmt | Technology | PIP Milestone 4 |  | FMEA & Quality plan - M4 | Which information are missing to give a commitment to deliver the new technology with TRL5 on time? - M3
| Deliverable | TM4.061.01 - TM4.061.01 |  | *Update Design FMEA *Check all Design-FMEA, i.e., on part level, measures for their status (Desing FMEA on part level) *Create a mitigation pactions which needs to be considered in further developemnt /productization |  | Project Mgmt | Quality | PIP Milestone 4 |  |  | Which PRS elements have not been qualified? - M4
| Deliverable | TM4.061.02 - TM4.061.02 |  | *verification of the FSR from technology and quality together *decision for release or release with condition or rejection |  | Project Mgmt | Quality | PIP Milestone 4 |  | IP Overview - M2 | Which PRS elements have not been qualified? - M4
| Deliverable | TM4.061.03 - TM4.061.03 |  | Updates of * potential analysis * measures defined, incl. status to ISO 9001 to be followed up in productization |  | Project Mgmt | Quality | PIP Milestone 4 |  | Software for development - M3 | Which PRS elements have not been qualified? - M4
| Epic | Supply Chain & Procurement for Productization prepared - M4 |  | * Check software releases available for the project * Define SW features and release version (What&When?) * If new software is needed for the project, update aligned timeline with the SW Project Management including releases for backlog topics |  |  |  | PIP Milestone 4 |  | Supply Chain & Procurement for Productization prepared - M4 | Which items of the handshake to PEP / PCM are not yet defined in the handover list? - M3
| Deliverable | TM4.071.01 - TM4.071.01 |  | * Long Lead items for Productization identified * All documents are prepared for order * or in follow up project |  | Project Mgmt | Purchasing | PIP Milestone 4 |  | IP Update - M3 | Which test cases have not been passed yet? - M4
| Epic | Project Controlling - M4 |  | All technical differences compared to the state fo the art (own technology as well as foreign technology) has been identified and listed |  | Intellectual Property | Technology | PIP Milestone 4 |  | Project Controlling - M4 | PRS - M3
| Deliverable | TM4.101.01 - TM4.101.01 |  | * validation of spent project costs |  | Project Mgmt | Controlling | PIP Milestone 4 |  | Supply Chain & Procurement for Development - M2 | Technology Qualification - M4
| Epic | FMEA & Qualityplan - M3 |  | Long Lead Item (LLI) list w/ suppliers created |  | Project Mgmt | Purchasing | PIP Milestone 3 |  | FMEA & Qualityplan - M3 | PRS - M2
| Deliverable | TM3.061.01 - TM3.061.01 |  | * Conduct Concept FMEA for the Technology ( for TRL4 only high level is needed) * Define mitigation measures * implementation of critical measues * Create a timeline and mitigation plan for those that are not yet implemented |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | Which PRS items are not yet updated? - M3
| Deliverable | TM3.061.02 - TM3.061.02 |  | *Update Design FMEA *Implement Design FMEA *Check all Design-FMEA, i.e., on part level, measures for their status (Desing FMEA on part level) *Create a timeline and mitigation plan for those that are not yet implemented |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | Which PRS items are not yet updated? - M3
| Deliverable | TM3.061.03 - TM3.061.03 |  | * Define / update a list of critical components * 100% verification of dimensions for all critical components * funtional tests done for functional units * If Final design loop: FSR required |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | Which PRS items are not yet updated? - M3
| Deliverable | TM3.061.04 - TM3.061.04 |  | * potential analysis completed * measures defined, incl. status to ISO 9001 |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | Which PRS items are not yet updated? - M3
| Epic | Supply Chain & Procurement for Qualification - M3 | [5 empty] | PIP Milestone 3 |  | Supply Chain & Procurement for Qualification - M3
| Deliverable | TM3.071.01 - TM3.071.01 |  | * List of suppliers defined * Aligned w/ purchasing |  | Purchasing | Technology | PIP Milestone 3 |  |  | Which PRS items are not yet linked to a test case? - M3
| Deliverable | TM3.071.02 - TM3.071.02 |  | * all parts needed for testing of the current development loop are available |  | Project Mgmt | Purchasing | PIP Milestone 3 |  |  | Which PRS items are not yet linked to a test case? - M3
| Deliverable | TM3.071.03 - TM3.071.03 |  | * Review current concept w/ Purchasing * Purchasing to provide their relevant requirements |  | Project Mgmt | Purchasing | PIP Milestone 3 |  |  | Which PRS items are not yet linked to a test case? - M3
| Epic | Operations - M3 | [5 empty] | PIP Milestone 3 |  | Operations - M3
| Deliverable | TM3.081.01 - TM3.081.01 |  | * Review current concept w/ Operations * Operations to provide their relevant requirements |  | Project Mgmt | Operations | PIP Milestone 3 |  |  | Which test cases have not been passed yet? - M3
| Epic | Service - M3 | [5 empty] | PIP Milestone 3 |  | Service - M3
| Deliverable | TM3.091.01 - TM3.091.01 |  | * Review current concept w/ Service * Service to provide their relevant requirements |  | Project Mgmt | Service | PIP Milestone 3 |  |  | Fast learning loops - M3

## Deliverable_Fields_Status
Fields | Status
Key | Template
Project Key | Deliverable Discussion
Issue Type | Deliverable Agreement
Summary | Deliverable Review
Description | Fulfilled
Reporter | Obsolete
PEP - Customer
PEP - Supplier
Fix Version/s
Epic Link
Epic Name
Status
Assignee
Due Date
Progress
Agreement
Result

## ExcelAddinMetadata (hidden)
R4J download fromjira
Sheet | Instance Name | URL | Username | Download Date | Selected Fields | Selected Filter | Selected Jql | Selected Project | Selected Tab | Enabled Settings
Tabelle3 | jira | https://jira.aixtron.com/jira/ | b.tauber@aixtron.com | 16:05 | ["Key","Project Key","Issue Type","Summary","Description","Fix Version/s","Reporter","PEP - Customer","PEP - Supplier","Epic Name","Epic Link"] | 0 | project="12808" | 12808 | 0 | {"SavePasswords":true,"ShowChangesAsComments":true,"ShowIssueKeysAsHyperlink":true}