## Upload_Template
Project Key | Issue Type | Summary | Key | Description | Reporter | PIP - Customer | PIP - Supplier | Fix Version/s | Epic Link | Epic Name | Epic Name Reference for Epic Linking
| Epic | Market expectations - M0 | [5 empty] | PIP Milestone 0 |  | Market expectations - M0
| Deliverable | TM0.011.01 - Market expectations defined? |  | * Describe the unmet or latent need of the market to our product which shall be addressed by the new Technology* Describe the value proposition that should be reached* When is expected to have the new technology available for the market? |  | PRG | MKT | PIP Milestone 0 |  |  | Market expectations - M0
| Epic | Preliminariy Timeline & Project Set up - M0 | [5 empty] | PIP Milestone 0 |  | Preliminariy Timeline & Project Set up - M0
| Deliverable | TM0.012.01 - Preliminary timeline until TM1 (MRS release) and PM defined? |  | *Plan Resources from technology for the MRS Phase… to start with a Draft of the PRS* name Project Manager and key experts* define Timeline, when MRS is ready* dedicated Budget only if >100'000 EUR are required |  | PRG | MKT | PIP Milestone 0 |  |  | Preliminariy Timeline & Project Set up - M0
| Epic | Project Motivation Presentation - M0 | [5 empty] | PIP Milestone 0 |  | Project Motivation Presentation - M0
| Deliverable | TM0.021.01 - Technology idea, Project objectives and scope and value proposition defined? |  | * Define highlevel the scope of the technology development - What is the idea for the technology? - What is the goal of the Project and what is in and out of scope? - Which learnings we would like to have achieved?* Formulate your hypothesis why it is a real demand, Why AIXTRON can win and why it should be worth doing it |  | MKT | PRG | PIP Milestone 0 |  |  | Project Motivation Presentation - M0
| Deliverable | TM0.021.02 - Program expectations defined ? |  | * Which product shall use the new technology?* Shall the new technology be handed over to and productized in a PEPor PCM Change (PDP-S)?* What is the expected TRL at handover?* What is the expected timeline until handover to the product? |  | MKT | PRG | PIP Milestone 0 |  |  | Project Motivation Presentation - M0
| Deliverable | TM0.021.03 - Project Motivation Presentation /MO released |  | *All above mentioned items to be presented in ONE ppt to Project Steering Committee (PSC) -> MO template* PSC releases all above mentioned items w/ M0, no extra signatures needed |  |  |  | PIP Milestone 0 |  |  | Project Motivation Presentation - M0
| Epic | Project number - M0 | [5 empty] | PIP Milestone 0 |  | Project number - M0
| Deliverable | TM0.101.01 - Project number assigned? |  | With M0 release the PSP number can be assigned |  | PM | CTRL | PIP Milestone 0 |  |  | Project number - M0
| Epic | MRS (80%) - M1 | [5 empty] | PIP Milestone 1 |  | MRS (80%) - M1
| Deliverable | TM1.011.01 - Which MRS items are not clear to the project team? |  | * Describe the gap in the market, i.e. the missing functions, not the solution concept.* Review MRS in Jira with the technology team for a common understanding, i.e., clarification of the degrees of freedom of technologies to define the solution* The content is sufficient for the project to start w/ first ideas and planning |  | Project Management | Product Marketing | PIP Milestone 1 |  |  | MRS (80%) - M1
| Deliverable | TM1.011.01 - Are joint development partners foreseen? |  | * Do we need development partners? If so who? and when to involve (right from the beginning or only for qualification?) |  | Project Management | Product Marketing | PIP Milestone 1 |  |  | MRS (80%) - M1
| Deliverable | TM1.011.02 - MRS-Baseline (80% maturity - 100% Scope) released? |  | * All MRS items are listed and "accepted" in Jira* 80% maturity accepted (at 100% Scope)* Release by sign-off of Jira-exported document by CEO, VP Marketing, VP Technology, VP Engineering, Program Manager, Produkt Manager |  | Project Management | Product Marketing | PIP Milestone 1 |  |  | MRS (80%) - M1
| Epic | Project planning M2 - M1 | [5 empty] | PIP Milestone 1 |  | Project planning M2 - M1
| Deliverable | TM1.031.01 - Project plan until TM2 created? |  | *Define the needed workpackages to TM2 (according checklist) and estimate the efforts * resources and staffing* timeline* estimation if budget of 100k€ is sufficent until TM2 -> if not PA is required. |  | Product Marketing | Project Management | PIP Milestone 1 |  |  | Project planning M2 - M1
| Epic | PA (Project Application) - M1 | [5 empty] | PIP Milestone 1 |  | PA (Project Application) - M1
| Deliverable | TM1.032.01 - Does the Phase from TM0 to TM2 require a budget >100k€? If so, has a PA until TM2 been signed yet? |  | *If initiatives directly related to the initialized project, such as LLI orders or early tests investigating general feasibility exceed the budget of 100k€ from TM0 to TM2 a preliminary project application is required. |  | Controlling | Project Management | PIP Milestone 1 |  |  | PA (Project Application) - M1
| Epic | MRS (100%) - M2 | [5 empty] | PIP Milestone 2 |  | MRS (100%) - M2
| Deliverable | TM2.011.04 - MRS-Baseline (100% Maturity) released? |  | * MRS finalized by Marketing - All MRS items are listed and "accepted" in Jira - 100% maturity accepted (at 100% Scope) |  | Project Management | Product Management | PIP Milestone 2 |  |  | MRS (100%) - M2
| Epic | Technology Sponsorship - M2 | [5 empty] | PIP Milestone 2 |  | Technology Sponsorship - M2
| Deliverable | TM2.021.01 - Did Project team agree on objectives and scope (incl. Definition of target TRL)? |  | Agreement between Program Manager & Project Manager (as representive of team) on objectives and scope. Program Mgr needs to make sure that TDP fits under program umbrella. |  | Product Mkt | Program Mgr | PIP Milestone 2 |  |  | Technology Sponsorship - M2
| Deliverable | TM2.021.02 - Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) |  | Program Management is accountable for regular update of project justification by answering the RWW questions:* REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution?*WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? |  | Program Mgr | Project Mgmt | PIP Milestone 2 |  |  | Technology Sponsorship - M2
| Epic | Project planning - M2 | [5 empty] | PIP Milestone 2 |  | Project planning - M2
| Deliverable | TM2.031.01 - Project plan for complete project defined? (incl. starting & end point, project strategy (e.g. # iterations) |  | * Project strategy defined - assumption of needed iterations of development cycles - internal development and/ or collaboration w/ externals - handover to productization - starting point and end point - TRL at project end (TRL5-> PEP & TRL>=6 -> PCM)* Project plan set up based on - work packages and efforts aligned w/ line managers - resources and staffing - summarized in a Work Breakdown Structure (WBS)* Budget for resources, external services, material and other costs* scheduling of Milestone Reviews incl. Previews 4 weeks ahead |  | Program Management (Technology Sponsor) | Project Mgmt | PIP Milestone 2 |  |  | Project planning - M2
| Deliverable | TM2.031.02 - Which risks have not been listed and assessed yet? (project risks and PRS risk assessment) |  | * Conduct risk assessment and mitigation based on Jira items* conduct risk assessment and mitigation of remaining topics based on the dashboard |  | Program Mgmt | Project Mgmt | PIP Milestone 2 |  |  | Project planning - M2
| Epic | PA (Project Application) - M2 | [5 empty] | PIP Milestone 2 |  | PA (Project Application) - M2
| Deliverable | TM2.032.01 - Project Application released? |  | Fill in the PA Template completely as per PA-instructions |  | Controlling | Project Mgmt | PIP Milestone 2 |  |  | PA (Project Application) - M2
| Epic | PRS - M2 | [5 empty] | PIP Milestone 2 |  | PRS - M2
| Deliverable | TM2.033.01 - Which parts of the MRS are not covered by the PRS? |  | *Translate all Marketing Requirements into Product Requirements *Using coverage level in JIRA*List requirments not covered in PRS*non-covered requirements to be presented in MRM (Milestone Release Meeting) |  | Product Mkt | Project Mgmt | PIP Milestone 2 |  |  | PRS - M2
| Deliverable | TM2.033.02 - Which stakeholders have not yet defined their requirements? |  | * Identify and define stakeholders (= not part of the project team) -> Marketing, Quality, Service, Purchasing* Request stakeholders to provide their relevant requirements and their experience/lessons learned * Project Team to provide leassons learned* Workshop with the aim to jointly prioritize provided lessons learned and requirements from the different stakeholders## if no Systems Engineer or Technologists from TechInnovation |  | Systems Engineering | Project Mgmt | PIP Milestone 2 |  |  | PRS - M2
| Deliverable | TM2.033.03 - PRS Baseline Released? |  | * All PRS requirements are entered in Jira * Review by Project team; if ok, Project manager or Systems engineer set requirement to "accepted"* All requirements must have status accepted (= requirement description done - not more) in Jira from all Stakeholders (TBD) -> defines baseline* Required signatures: TDP project team, Project Manager, Program Manager, Product Mgr, Mgr Technology Innovation*Signature to be performed directly in Jira using baselines |  | Program Mgr | Project Mgmt | PIP Milestone 2 |  |  | PRS - M2
| Epic | Proof of Concept Testing - M2 | [5 empty] | PIP Milestone 2 |  | Proof of Concept Testing - M2
| Deliverable | TM2.041.01 - Which key questions (e.g. on feasibility/cost/strategic) are crucial for the project (so called red flags) and have not yet been answered? |  | * Indentify the real important questions on technical and economical feasibility which are a thread to the whole project needs to be answered as soon as possible* Proof-of-Concept testing - if beneficial, fast PoC tests can be initiated already in TM2 phase. - These tests can provide crucial input for project planning |  | Project Mgmt | Technology | PIP Milestone 2 |  |  | Proof of Concept Testing - M2
| Deliverable | TM2.041.02 - For which key questions are no preliminary red flag test defined? |  | * Plan simple but convincing feasibility tests to mitigate the red flags* Start testing immediately |  | Project Mgmt | Technology | PIP Milestone 2 |  |  | Proof of Concept Testing - M2
| Epic | Technology Development (Problem-Analysis, first ideas and solution space) - M2 | [5 empty] | PIP Milestone 2 |  | Technology Development (Problem-Analysis, first ideas and solution space) - M2
| Deliverable | TM2.042.01 - Which parts of the problem has not been analyzed and formulated in a problem statement yet? |  | * systematic analysis of the problem/ of the technical system - what is the real problem? - What is the root cause? - Which parameters can be used to improve the technology? - what are the boundary conditions?* clear problem statement |  | Project Mgmt | Technology | PIP Milestone 2 |  |  | Technology Development (Problem-Analysis, first ideas and solution space) - M2
| Deliverable | TM2.042.02 - Has first ideas been gathered? |  | * State of the art analysis ->Before developing something new the state of the art has to be understood* Brainstorming of first ideas / collecting ideas from former projects -> Be careful: This does not replace a systematic concept development |  | Project Mgmt | Technology | PIP Milestone 2 |  |  | Technology Development (Problem-Analysis, first ideas and solution space) - M2
| Deliverable | TM2.042.03 - For which technologies could a solution path not yet be defined? |  | * TRL and feasibility assessment of first ideas* Pre-selection of most promising ideas * sketch technical solution path for Technology development -> serves as basis for planning |  | Project Mgmt | Technology | PIP Milestone 2 |  |  | Technology Development (Problem-Analysis, first ideas and solution space) - M2
| Epic | Effects on Software - M2 | [5 empty] | PIP Milestone 2 |  | Effects on Software - M2
| Deliverable | TM2.044.01 - For which key functions and key components has the influence on software not been checked? |  | * Check if the drafted solution path requires software development or adaptions* incorporate into planning accordingly |  | Project Mgmt | Software Development | PIP Milestone 2 |  |  | Effects on Software - M2
| Epic | IP Overview - M2 | [5 empty] | PIP Milestone 2 |  | IP Overview - M2
| Deliverable | TM2.051.01 - IP Overview created (State of the Art)? |  | * IP landscape research based on idea portfolio* overview created about relevant IP in this field |  | Technology | Intellectual Property | PIP Milestone 2 |  |  | IP Overview - M2
| Deliverable | TM2.051.02 - FTO for initial ideas / solution space? |  | * IP reviewed by Project team - which ideas can be used? - which patents are blocking?* FTO for solution space. If not new ideas has to be developed. |  | Project Mgmt | Intellectual Property | PIP Milestone 2 |  |  | IP Overview - M2
| Epic | FMEA & Quality plan - M2 | [5 empty] | PIP Milestone 2 |  | FMEA & Quality plan - M2
| Deliverable | TM2.061.01 - if target TRL >=5 LLI Supplier qualification: potential analysis completed and (if required) measures defined? |  | If the targeted TRL of the new Technology is >=5 (at the next iteration loop) it is necessary to do verify, if the selected supplier can deliver the expected quality. This is covered by the potential analysis |  | Project Mgmt | Quality | PIP Milestone 2 |  |  | FMEA & Quality plan - M2
| Epic | Supply Chain & Procurement for Development - M2 | [5 empty] | PIP Milestone 2 |  | Supply Chain & Procurement for Development - M2
| Deliverable | TM2.071.01 - Which components or materials with long lead times need an early order? |  | Long Lead Item (LLI) list w/ suppliers created |  | Project Mgmt | Purchasing | PIP Milestone 2 |  |  | Supply Chain & Procurement for Development - M2
| Epic | Technology Sponsership - M3 | [5 empty] | PIP Milestone 3 |  | Technology Sponsership - M3
| Deliverable | TM3.021.01 - Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) |  | Program Management is accountable for regular update of project justification by answering the RWW questions:* REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution?*WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? |  | Program Mgr | Project Mgmt | PIP Milestone 3 |  |  | Technology Sponsership - M3
| Epic | Technical & economic viability assessment & Project & Risk Mamagement - M3 | [5 empty] | PIP Milestone 3 |  | Technical & economic viability assessment & Project & Risk Mamagement - M3
| Deliverable | TM3.031.01 - Project plan (timeline and budget) updated until TM4? |  | * Monthly update of project plan expected - scope & early testing - number of development loops - timeline - resources - budget - test cases and need test rigs - required lab time & resources* Project manager updates the timeline based on updated the timelines of work packages (should be done within the team)* Including Software Release plan due to project timeline * Communicate the effects of changes in the project plan from the current phase to everyone affected by the impact * Milestone Preview (4-6 Weeks prior to Review) |  | Program Mgr | Project Mgmt | PIP Milestone 3 |  |  | Technical & economic viability assessment & Project & Risk Mamagement - M3
| Deliverable | TM3.031.02 - Which risks are pending regarding assessment and mitigation? (Project and PRS risks) |  | *Alignment PRS with results of the current phase, e.g. test results, FMEA Measures, built issues, etc.* Update risk assessment and mitigation based on Jira items* Update risk assessment and mitigation of remaining topics based on the dashboard |  | Program Mgr | Project Mgmt | PIP Milestone 3 |  |  | Technical & economic viability assessment & Project & Risk Mamagement - M3
| Deliverable | TM3.031.03 - Which information are missing to give a commitment to deliver the new technology with TRL5 on time? |  | Assess how much confidence we gained to achieve TRL5 on time.Which investigatios or test results are missing to give a commitment? Which uncertainties remain?Clearly show, which results gives conficence to deliver on time. |  | Program Mgr | Project Mgmt | PIP Milestone 3 |  |  | Technical & economic viability assessment & Project & Risk Mamagement - M3
| Deliverable | TM3.031.04 - Which items of the handshake to PEP / PCM are not yet defined in the handover list? |  | The technology needs to be handed over properly to a either a PCM or PEP for productization. All items needs to be defined in the TDP Handover List, as- links to a technical file describing the developement of the technology and related learnings,- all design documents (BOM, drawings)- Supporting documents or TAs for assembly and integration- Shop floor test instructions- Part quality and supplier information- SW documentation... |  | Program Mgr | Project Mgmt | PIP Milestone 3 |  |  | Technical & economic viability assessment & Project & Risk Mamagement - M3
| Epic | PRS - M3 | [5 empty] | PIP Milestone 3 |  | PRS - M3
| Deliverable | TM3.033.01 - Which PRS items are not yet updated? |  | * It is likely that learnings during technology development lead to changes or refinement of requirements in PRS. Hence, with each development loop the requirements should be reviewed and updated if required |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | PRS - M3
| Deliverable | TM3.033.02 - Which PRS items are not yet linked to a test case? |  | * Define a relevant test case for technical PRS items in Jira* Ensure the required test environment in coordination with the parties concerned, such as the laboratory* Ensure an all encompassing test concept for qualification phase to ensure fullfillement of each requirement of the PRS |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | PRS - M3
| Deliverable | TM3.033.03 - Which test cases have not been passed yet? |  | Evaluation of test results and comparison with MRS and PRS *root cause analysis for unsuccessfull test results*create back log list for further improvement *open issues from the back log list must be assigned and solutions developed |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | PRS - M3
| Epic | Fast learning loops - M3 | [5 empty] | PIP Milestone 3 |  | Fast learning loops - M3
| Deliverable | TM3.041.01 - Which (key) functions / hypotheses are not proven yet by the learning loops? |  | * Make sure that the tests / investigations answering the key questions are handled with priority* each key question shall be answered and well documented in a Technical Investigation Report |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Fast learning loops - M3
| Deliverable | TM3.041.02 - Which red flag test are not passed? |  | * Analyse why tests have not been passed* Derive learning* Review and update risk analysis accordingly |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Fast learning loops - M3
| Epic | Technology Development - M3 | [5 empty] | PIP Milestone 3 |  | Technology Development - M3
| Deliverable | TM3.042.01 - Which individual concepts for the required functions are not yet finalized and aligned with each other and the overall concept? |  | * Create a Functional model for the new Technology or provide Functional Analysis for the given problem* Develop various solution alternatives for the individual functions -> Morphological Box* Combine individual solutions into a few meaningful overall concepts * Assessment of concepts based on defined criteria and selection of most promising* Work out the concept as far as needed to answer PRS coverage, considering - key requirements and solved key questions - expected process performance, - integration into target system and interfaces, - Manufacturability, - assembly and test - software - Serviceability |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Technology Development - M3
| Deliverable | TM3.042.02 - Which PRS items are not fullfilled by the concept? |  | * Check if the Concept fulfills all PRS requirements* Document results and degree of fullfillment-> as input for Concept Review Meeting |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Technology Development - M3
| Deliverable | TM3.042.03 - Which concept review actions are still open? |  | * Conduct Concept Review Workshop with experts and relevant stakeholders* Review the complete concept on component level - Concept alternatives checked - Feasibility of key functions checked - Preliminary Supplier shortlist developed - Make or buy decided* Concept Risk Review-Event conducted* Concept by Program& Product Marketing approved* Planning & Risk Mitigation Event conducted* Define open actions |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Technology Development - M3
| Deliverable | TM3.042.04 - Which Technological Learnings are not documented in a technical investigation report? |  | Document the key learnings in a comprehensive Technical Investigation Report |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Technology Development - M3
| Epic | Design review & release (if target TRL >=5) - M3 | [5 empty] | PIP Milestone 3 |  | Design review & release (if target TRL >=5) - M3
| Deliverable | TM3.043.01 - Which individual designs according to Engineering BoM are not yet finalized? (if TRL >= 5) |  | Design for the whole technology is done, including* all CAD models* calculations and simulation reports* interfaces defiend and checked* Changes in basic documents updated and released: Gas-mixing-circuit, cooling circuit, vacuum circuit, floor plan, E-Plan, Network System List (NSL)* Supplier feedback on parts design collected, assessed and implemented * BoM cost estimation for design |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Design review & release (if target TRL >=5) - M3
| Deliverable | TM3.043.02 - Which PRS items are not fullfilled by the designed Technology? |  | * Check if the design fulfills all PRS requirements* Document results and degree of fullfillment-> as input for Design Review Meeting |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Design review & release (if target TRL >=5) - M3
| Deliverable | TM3.043.03 - Which critical design review actions are still open? |  | * Conduct Design Review Workshop with experts and relevant stakeholders* Review the complete design on component level - Feasibility of key functions checked - Supplier shortlist developed* Design FMEA input considered* Define open actions |  | Project Mgmt | Technology | PIP Milestone 3 |  |  | Design review & release (if target TRL >=5) - M3
| Deliverable | TM3.043.04 - Which departments have not yet released the design? |  | *All critical actions form design review are done* Minor actions are planned in further developement* Design released by whole TDP team and Program Mgr, Sen Mgr TechDev |  | Program Mgmt | Project Mgmt | PIP Milestone 3 |  |  | Design review & release (if target TRL >=5) - M3
| Epic | Software for development - M3 | [5 empty] | PIP Milestone 3 |  | Software for development - M3
| Deliverable | TM3.044.01 - Which software packages for development and testing are not available? |  | * Check software releases available for the project* Define SW features and release version (What&When?)* If new software is needed for the project, update aligned timeline with the SW Project Management including releases for backlog topics |  |  |  | PIP Milestone 3 |  |  | Software for development - M3
| Epic | IP Update - M3 | [5 empty] | PIP Milestone 3 |  | IP Update - M3
| Deliverable | TM3.051.01 - LoD (List of Differences?) completed? |  | All technical differences compared to the state fo the art (own technology as well as foreign technology) has been identified and listed |  | Intellectual Property | Technology | PIP Milestone 3 |  |  | IP Update - M3
| Deliverable | TM3.051.02 - FTO for all identified solutions ? |  | - LoD (List of Differences?) defined?- IP Targets defined?- Can we achieve IP protection?- Do all identified solutions have Freedom to operate? |  | Project Mgmt | Intellectual Property | PIP Milestone 3 |  |  | IP Update - M3
| Epic | FMEA & Qualityplan - M3 | [5 empty] | PIP Milestone 3 |  | FMEA & Qualityplan - M3
| Deliverable | TM3.061.01 - Concept FMEA conducted and measures implemented? (TRL4: only high level) |  | * Conduct Concept FMEA for the Technology( for TRL4 only high level is needed)* Define mitigation measures* implementation of critical measues * Create a timeline and mitigation plan for those that are not yet implemented |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | FMEA & Qualityplan - M3
| Deliverable | TM3.061.02 - If TRL>=5: Which design elements are not considered in the D-FMEA and which D-FMEA measures are not implemented? |  | *Update Design FMEA*Implement Design FMEA*Check all Design-FMEA, i.e., on part level, measures for their status (Desing FMEA on part level)*Create a timeline and mitigation plan for those that are not yet implemented |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | FMEA & Qualityplan - M3
| Deliverable | TM3.061.03 - Which crititical parts do not have a 100% verification of dimensions + functional test (pre-sample)? If Final design loop: FSR required. |  | * Define / update a list of critical components* 100% verification of dimensions for all critical components * funtional tests done for functional units* If Final design loop: FSR required |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | FMEA & Qualityplan - M3
| Deliverable | TM3.061.04 - If TRL>=5: Which suppliers have not been qualified yet? Which of them do not have the potential to be qualified? |  | * potential analysis completed * measures defined, incl. status to ISO 9001 |  | Project Mgmt | Quality | PIP Milestone 3 |  |  | FMEA & Qualityplan - M3
| Epic | Supply Chain & Procurement for Qualification - M3 | [5 empty] | PIP Milestone 3 |  | Supply Chain & Procurement for Qualification - M3
| Deliverable | TM3.071.01 - Supplier selection aligned with Purchasing? |  | * List of suppliers defined* Aligned w/ purchasing |  | Purchasing | Technology | PIP Milestone 3 |  |  | Supply Chain & Procurement for Qualification - M3
| Deliverable | TM3.071.02 - Prototype procurement completed (per Loop)? |  | * all parts needed for testing of the current development loop are available |  | Project Mgmt | Purchasing | PIP Milestone 3 |  |  | Supply Chain & Procurement for Qualification - M3
| Deliverable | TM3.071.03 - Which stakeholder requirements from Purchasing are not defined yet? (with TRL5) |  | * Review current concept w/ Purchasing * Purchasing to provide their relevant requirements |  | Project Mgmt | Purchasing | PIP Milestone 3 |  |  | Supply Chain & Procurement for Qualification - M3
| Epic | Operations - M3 | [5 empty] | PIP Milestone 3 |  | Operations - M3
| Deliverable | TM3.081.01 - Which stakeholder requirements from Operations are not defined yet? (with TRL5) |  | * Review current concept w/ Operations * Operations to provide their relevant requirements |  | Project Mgmt | Operations | PIP Milestone 3 |  |  | Operations - M3
| Epic | Service - M3 | [5 empty] | PIP Milestone 3 |  | Service - M3
| Deliverable | TM3.091.01 - Which stakeholder requirements from Service are not defined yet? (with TRL5) |  | * Review current concept w/ Service * Service to provide their relevant requirements |  | Project Mgmt | Service | PIP Milestone 3 |  |  | Service - M3
| Epic | Technology Sponsorship - M4 | [5 empty] | PIP Milestone 4 |  | Technology Sponsorship - M4
| Deliverable | TM4.021.01 - Does the technical & economic viability assessment justify continuation of the existing plan or does it need to be adapted or changed? (RWW) |  | Program Management is accountable for regular update of project justification by answering the RWW questions:* REAL? Is there a real need at the market? Is the problem we try to solve or the envisioend benefit real? Are customers are willing to pay for our solution? * WIN? can we deliver the added value we are aiming for with the new technology? is it feasible within the given time? Will customers accept our solution?*WORTH IT? Is it worth spending the real costs and the opportunity costs for this Technology? |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  |  | Technology Sponsorship - M4
| Epic | Project planning - M4 | [5 empty] | PIP Milestone 4 |  | Project planning - M4
| Deliverable | TM4.031.01 - Which risks are pending regarding update of assessment and mitigation? (Project and PRS risks) |  | *Alignment PRS with results of the current phase, e.g. test results, FMEA Measures, built issues, etc.* Update risk assessment and mitigation based on Jira items* Update risk assessment and mitigation of remaining topics based on the dashboard |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  |  | Project planning - M4
| Deliverable | TM4.031.02 - Lessons learned done and communicated? |  | * lessons Learned session with project team and relevant stakeholders done* results documented and communicated |  | Program Mgr | Project Mgmt | PIP Milestone 4 |  |  | Project planning - M4
| Deliverable | TM4.031.03 - Which stakeholders have not yet released the handover list? |  | *A Handover list completed * List of open issues assigend to responsible (supplier in the phase of productization)* all project closing relevant tasks fulfilled* sign-off by customer |  | Program Mgr / PEP PM | Project Mgmt | PIP Milestone 4 |  |  | Project planning - M4
| Epic | PRS - M4 | [5 empty] | PIP Milestone 4 |  | PRS - M4
| Deliverable | TM4.033.01 - Which PRS elements have not been qualified? |  | *check final qualification status on PRS Level |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | PRS - M4
| Deliverable | TM4.033.02 - Which test cases have not been passed yet? |  | Evaluation of test results and comparison with MRS and PRS *root cause analysis for unsuccessfull test results*create back log list for further improvement *open issues from the back log list must be assigned and solutions developed |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | PRS - M4
| Epic | Technology Qualification - M4 | [5 empty] | PIP Milestone 4 |  | Technology Qualification - M4
| Deliverable | TM4.041.01 - Final Technology Qualification review performed and TRL target achieved? |  | * conduct Review of all qualification results* identify gaps to targeted TRL* define measures * re-iterate development if needed |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Technology Qualification - M4
| Deliverable | TM4.041.02 - If target TRL7: customer feedback received |  | * tested at customer and feedback receivede.g. wishes for product improvememt |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Technology Qualification - M4
| Epic | Technology Development - achieving TRL5/6 and documentation - M4 | [5 empty] | PIP Milestone 4 |  | Technology Development - achieving TRL5/6 and documentation - M4
| Deliverable | TM4.042.01 - Final design report released? |  | * Final design reported created/updated (shows final design)* released |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Technology Development - achieving TRL5/6 and documentation - M4
| Deliverable | TM4.042.02 - Which technological learnings are not documented in the Technology Development File? |  | * update of Technical Development File report by qualification results and latest learnings (shows design incl. all relevant learnings - to preserve the knowledge) |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Technology Development - achieving TRL5/6 and documentation - M4
| Deliverable | TM4.042.03 - Which parts of the documents according handover list are still missing? (e.g. BoM, models, drawings, Work instructions) |  | * review items of handover list individually with receiwing project/customer* list is complete |  | Project Mgmt | Technology | PIP Milestone 4 |  |  | Technology Development - achieving TRL5/6 and documentation - M4
| Epic | Software for qualification - M4 | [5 empty] | PIP Milestone 4 |  | Software for qualification - M4
| Deliverable | TM4.044.01 - Which software packages for qualification or productization are not available? |  | *Update check of software releases available for productization |  | Project Mgmt | Software Development | PIP Milestone 4 |  |  | Software for qualification - M4
| Epic | IP Update - M4 | [5 empty] | PIP Milestone 4 |  | IP Update - M4
| Deliverable | TM4.051.01 - LoD reviewed and updated? |  | * Make sure that LoD is up to date |  | Intellectual Property | Technology | PIP Milestone 4 |  |  | IP Update - M4
| Deliverable | TM4.051.02 - FTO reviewed and updated? |  | * Make sure that FTO for the whole technology exists |  | Project Mgmt | Intellectual Property | PIP Milestone 4 |  |  | IP Update - M4
| Epic | FMEA & Quality plan - M4 | [5 empty] | PIP Milestone 4 |  | FMEA & Quality plan - M4
| Deliverable | TM4.061.01 - D-FMEA finalized and actions executed? |  | *Update Design FMEA*Check all Design-FMEA, i.e., on part level, measures for their status (Desing FMEA on part level)*Create a mitigation pactions which needs to be considered in further developemnt /productization |  | Project Mgmt | Quality | PIP Milestone 4 |  |  | FMEA & Quality plan - M4
| Deliverable | TM4.061.02 - Which First Sample Reports (FSR) are not released? |  | *verification of the FSR from technology and quality together*decision for release or release with condition or rejection |  | Project Mgmt | Quality | PIP Milestone 4 |  |  | FMEA & Quality plan - M4
| Deliverable | TM4.061.03 - If TRL>=5: Which suppliers have not been qualified yet? |  | Updates of* potential analysis * measures defined, incl. status to ISO 9001to be followed up in productization |  | Project Mgmt | Quality | PIP Milestone 4 |  |  | FMEA & Quality plan - M4
| Epic | Supply Chain & Procurement for Productization prepared - M4 | [5 empty] | PIP Milestone 4 |  | Supply Chain & Procurement for Productization prepared - M4
| Deliverable | TM4.071.01 - Procurement prepared for Productization |  | * Long Lead items for Productization identified* All documents are prepared for order* or in follow up project |  | Project Mgmt | Purchasing | PIP Milestone 4 |  |  | Supply Chain & Procurement for Productization prepared - M4
| Epic | Project Controlling - M4 | [5 empty] | PIP Milestone 4 |  | Project Controlling - M4
| Deliverable | TM4.101.01 - Project Costs validation done? |  | * validation of spent project costs |  | Project Mgmt | Controlling | PIP Milestone 4 |  |  | Project Controlling - M4

## Deliverable_Fields_Status
Fields | Status
Key | Template
Project Key | Deliverable Discussion
Issue Type | Deliverable Agreement
Summary | Deliverable Review
Description | Fulfilled
Reporter | Obsolete
PEP - Customer
PEP - Supplier
Fix Version/s
Epic Link
Epic Name
Status
Assignee
Due Date
Progress
Agreement
Result

## ExcelAddinMetadata (hidden)
R4J download fromjira
Sheet | Instance Name | URL | Username | Download Date | Selected Fields | Selected Filter | Selected Jql | Selected Project | Selected Tab | Enabled Settings
Tabelle3 | jira | https://jira.aixtron.com/jira/ | b.tauber@aixtron.com | 16:05 | ["Key","Project Key","Issue Type","Summary","Description","Fix Version/s","Reporter","PEP - Customer","PEP - Supplier","Epic Name","Epic Link"] | 0 | project="12808" | 12808 | 0 | {"SavePasswords":true,"ShowChangesAsComments":true,"ShowIssueKeysAsHyperlink":true}